## Town Hall 2024
ACTION NUMBER | DATE ADDED | RESOLVED | FROM | ACTION | TARGET DATE | NOTES | STATUS | COMPLETION DATE | SUPPLIER | OWNER
MEETING RESOLUTIONS
2024/1 | 2024-02-07 | 2024-02-06 | Cllr Wilson | Prepare Bookings Report | 2024-03-26 | Detailed report | Completed |  | Town Hall | Clair
2024/2 | 2024-02-07 | 2024-02-06 | Committee | Promote Town Hall as Wedding Venue | 2024-11-20 | Community Engagement | Ongoing |  | Town Hall | Tom
2024/3 | 2024-02-07 | 2024-02-06 | Committee | Consider changing meeting Dates & Frequency | 2024-05-22 | Annual Meeting | Ongoing |  | Town Hall | Cathy
| 2024-02-07 | 2024-02-06 | Committee | Investigate food hygeine courses | 2024-03-31 | https://checkout.highspeedtraining.co.uk/checkout Waiting on the go ahead to pay | Completed | Waiting on the go ahead to pay | High Speed Training | Clair
2023/22 | 2023-07-18 | 2024-07-04 | Ian Watkins | Prepare schedule to promote awareness days | 2024-02-13 | Community Engagement | Pending |  | Town Hall | Tom
2023/23 | 2023-07-06 | 2024-07-04 | Ian Watkins | Community Cinema | 2024-09-01 | Community Engagement | Pending | Meeting arraneed will update | Town Hall | Clair/Tom/Ian
2023/26 | 2023-12-06 | 2023-12-05 | Committee | Action recommendations for improving safety in clock tower | 2024-03-31 | Tim & Baz to action | Pending |  | Best Clock Man | Clair
2023/25 | 2023-12-06 | 2023-12-05 | Committee | Original Clock Mechanism | 2024-02-29 | Visit from Museum arranged 13 Feb | Ongoing | please find attahced email from St Fagasn s | St Fagans Museum | Cathy
|  |  |  | Update Scribe with payments and receipts | Daily | Keep daily log | Daily | Daily | Scribe | Clair
|  |  |  | take phtos and market the halls and chambers for weddings |  |  | pending |  |  | Clair/Tom
DAILY TASKS
|  |  |  | Cleaning of kitchen and bathroom areas | Daily | Keep daily log | Daily | Daily | Town Hall | Baz/Tim
|  |  |  | Set up, clean and oversee rooms for hire | Daily | Keep daily log | Daily | Daily | Town Hall | Baz/Tim
|  |  |  | Moderate heating depending on the weather | Daily | Keep daily log | Daily | Daily | Town Hall | Baz/Tim
|  |  |  | Chase outstanding invoices | Daily | Keep daily log | Daily | Daily | Scribe | Clair
|  |  |  | Update notice boards | Daily |  | Daily | Daily | Cowbridge TC | Clair
|  |  |  | Finance Reports | [5 empty] | Clair
WEEKLY TASKS
|  |  |  | Test fire alarms | Weekly | Record checks in book | Weekly | Weekly |  | Baz/Tim
|  |  |  | Run water from all taps in unused areas & check temperature | Weekly | Record checks in book | Weekly | Weekly |  | Baz/Tim
|  |  |  | Polishing Lesser and Main hall Floors | Weekly |  | Weekly | Weekly |  | Baz/Tim
|  |  |  | Vacuuming office, chamber, parlour, robing room, lesser hall lounge | Weekly |  | Weekly | Weekly |  | Baz/Tim
|  |  |  | Cleaning out front, bench, notice boards, steps, immediate footpath area | Weekly |  | Weekly | Weekly
|  |  |  | Checking of flags and flag poles | Weekly |  | Weekly | Weekly
|  |  |  | Checking War Memorial | Weekly |  | Weekly | Weekly |  | Tim/Baz
MONTHLY TASKS
|  |  |  | Minutes | [5 empty] | Cathy
|  |  |  | Agendas | [5 empty] | Cathy
|  |  |  | Town Hall Invoicing | [5 empty] | Clair
|  |  |  | Send end of month booking report to all hirers | [5 empty] | Clair
|  |  |  | Water treatment | TBC | Check when last carried out | Complete | 2023-09-01 | JD Water Consultants | Clair
|  |  |  | Defibrillator Check | [5 empty] | Freemasons
Check
ADDED BY OFFICERS
|  |  | Dave Breen | Stop Cocks | 2024-03-31 |  |  |  |  | Baz/Tim
|  |  | Dave Breen | Electric Trip Switches | 2024-03-31 |  |  |  |  | Baz/Tim
|  |  | Dave Breen | Update meter supplier list | 2024-03-31 |  |  |  |  | Baz/Tim
|  |  | Cathy Kennedy | Prepare accessible access policy | 2024-03-31 |  |  |  |  | Cathy/Clair
ANNUAL TASKS
|  |  |  | Fire Extinguisher service | TBC | Check when last carried out | Complete | 2023-03-01 | Tremorfa | Clair
|  |  |  | Lift Service | 2024-02-06 | Gartec | Complete | 2024-02-06 | Gartec | Clair
|  |  |  | PAT Testing | 2024-03-31 | Source supplier | Pending |  |  | Clair
2023/24 | 2023-07-06 | 2024-07-04 | John Andrew | Prepare Coronation Collage | 2024-04-30 | Cost may exceed 2023/24 Budget | Pending |  | Town Hall | Clair/Tom