## Meeting Actions
Date added | Lead | Meeting | Actions | Target Date
11th July 2023 | Clair | L&A | Add date column to action plan | 30.11.2024 | Complete
11th July 2023 | Cathy | L&A | Double the budget for the Holy Cross Churchyard due to a crumbling wall | 30.11.2024 | Complete
11th July 2023 | Charles | L&A | Set up a s106 Task & FinishGroup | 31.01.2024 | Complete TOR to be approved
11th July 2023 | Clair | L&A | Increase the Limes Cemetery Charges by 5%, from 1 April 2024 | 31.03.2024 | Complete
9th January 2024 | Clair | L&A | Quotes to repair crumbling wall in the Holy Cross | 2024-05-30
9th January 2024 | Clair | L&A | Letter drop to advise against using bins | 2024-05-30 | Trialing to remove the bin
9th January 2024 | Clair | L&A | Price to replace gate in Llanbethian Park | 2024-05-30 | In progress
31st January 2024 | Clair | L&A | Replace bins with recycle bins | 31/03/2024 | Only applies to work places, town hall office has new bins
5th March 2024 | Charles & Biga | L&A | Charles & Biga to oversee donation of trees to the council | 2024-04-30 | Complete

## Officer Actions
Leisure & Amenities Action Plan
Action no | Date added | From | Action | Target date | Notes | Private notes | RAG | Priority | Deadline | Status | Owner
1 |  | L&A | SOUTHGATE PARK
|  |  | Bins | 05.01.2024 | Daily |  |  |  |  | Ongoing | Tim
|  |  | Hedge and Tree maintenance | 30.09.2024 | Quarterly |  |  |  |  | Pending | Tim
|  |  | Grass Cutting | 30.09.2024 | April - October |  |  |  |  | Pending | Edenvale
|  |  | Bench Maintenance | 05.01.2024 | Weekly |  |  |  |  | Ongoing | Tim
|  |  | Tree Maintenance | 30.09.2024 | Annually |  |  |  |  | Pending | ESA
2 |  | L&A | LLANBLETHIAN PLAYING FIELDS
|  |  | Play Park Checks | 31.01.2024 | Monthly |  |  |  |  | Ongoing | Urban Recreation
|  |  | Bins | 05.01.2024 | Twice weekly |  |  |  |  | Ongoing | Tim
|  |  | Apple Tree Whips | 30.09.2024 | Start June dependent on weather |  |  |  |  | Pending | Tim
|  |  | Hedge Maintenance | 30.11.2024 | [5 empty] | Pending | Tim
|  |  | General cleaning and bench maintenance | 05.01.2024 | Weekly |  |  |  |  | Ongoing | Tim
|  |  | Tree Maintenance | 31.07.2024 | Annually |  |  |  |  | Pending | ESA
3 |  | L&A | TWT PARK
|  |  | Play Park Checks/maintenance | 31.01.2024 | Monthly |  |  |  |  | Ongoing | Urban Recreation
|  |  | Bins | Daily | Daily |  |  |  |  | Ongoing | Tim
|  |  | Leaf cleaning | 31.10.2024 | Autumn |  |  |  |  | Pending | Tim
|  |  | General tidying and maintenance | Daily | Daily |  |  |  |  | Ongoing | Tim
|  |  | Tree Maintenance | 31.10.2024 | Annually |  |  |  |  | Pending | ESA
|  |  | Rose Beds | 01.07.2024 | Summer |  |  |  |  | Pending | Tim
|  |  | Grass Cutting | 31.10.2024 | April - October |  |  |  |  | Pending | Edenvale
|  |  | Hedge Cutting | 31.10.2024 | Quarterly |  |  |  |  | Pending | Tim
|  |  | Puddle behind Waitrose and adjacent to Twt park | 30.04.2024 | Vale Consultancy report |  |  |  |  | Ongoing | Full Council
4 |  | L&A | THE LIMES CEMETERY
|  |  | Grass Cutting | 31.10.2024 | April - October 2023 |  |  |  |  | Pending | Edenvale
|  |  | Bins | Daily | [5 empty] | Ongoing | Tim
|  |  | Hedge Cutting | 31.10.2024 | Spring and Autumn |  |  |  |  | Ongoing | Tim
|  |  | Leaf Blowing | 31.10.2024 | Autumn |  |  |  |  | Pending | Tim
|  |  | Plants | 31.10.2024 | Spring and Autumn |  |  |  |  | Pending | Tim
|  |  | Benches | Weekly | Weekly cleaning/maintenance |  |  |  |  | Ongoing | Tim
|  |  | Memorial Safety Check | 31.10.2024 | Every 5 years due 2024 (draw up plan) |  |  |  |  | Ongoing | Tim/Cathy
|  |  | Tree Maintenance | 31.10.2024 | Annually - completed October 2023 |  |  |  |  | Pending | ESA
5 |  | L&A | HOLY CROSS CHURCHYARD
|  |  | Memorial Safety Check | 01.07.2028 | Every 5 years check completed July 2023 (Draw up plan) |  |  |  |  | Pending | Cathy
|  |  | Memorial Safety repairs/Maintenance | 01.07.2028 | Any Actions |  |  |  |  | Pending | Cathy
|  |  | Grass Cutting | 31.10.2024 | April - October |  |  |  |  | Pending | Edenvale
|  |  | Ornamental Hedge Cutting | 01.11.2024 | Spring and Autumn |  |  |  |  | Pending | Tim/Baz
|  |  | Tree Maintenance | 01.11.2024 | Annually |  |  |  |  | Pending | ESA
|  |  | General cleaning and maintenance when required | 31.01.2024 | Monthly |  |  |  |  | Pending | Tim
6 |  | L&A | PICCADILLY
|  |  | Grass Cutting | 01.11.2024 | April - October |  |  |  |  | Pending | Edenvale
|  |  | Tree Maintenance | 01.11.2024 | Annually |  |  |  |  | Pending | ESA
7 |  | L&A | EMMS COTTAGE
|  |  | Shrub maintenance | 01.11.2024 | Annually in the Autumn/Winter |  |  |  |  | Pending | Tim
8 |  | L&A | THE LIMES SHED
|  |  | Maintain Limes Shed | Weekly | Ongoing |  |  |  |  | Ongoing | Tim
|  |  | Maintaining parking area, planters and bench | Weekly | Ongoing |  |  |  |  | Ongoing | Tim
|  |  | Pay final bill and arrange meter removal | 31.01.2024 | EON to disconnect 5th January |  |  |  |  | complete | Clair
9 |  | L&A | RIVERSIDE
|  |  | Planting of Pots & Watering | 30.09.2024 | Panted Spring and Autumn, watered throughout Summer |  |  |  |  | Pending | Tim
10 |  | L&A | WEEKLY TASKS
|  |  | Check Defibs | Weekly | Check battery and non tampering |  |  |  |  | Ongoing | Tim
11 |  | L&A | Every other Month
|  |  | Minutes | 7 days after | January |  |  |  |  | Ongoing | Cathy
|  |  | Agendas | 7 days before | January |  |  |  |  | Ongoing | Cathy
|  |  | Finance Reports | 7 days before | January |  |  |  |  | Ongoing | Clair
12 |  |  | ANNUAL TASKS
|  | Bio-diversity | Bio-diversity report | 31.07.2024 | [5 empty] | Pending | Cathy
|  | Bio-diversity | Order Summer Baskets | 31.03.2024 | Order March 2024 |  |  |  |  | Complete | Cathy
|  | Statutory | Prepare Budget & Precept Request | 31.10.2024 | [5 empty] | Complete | Cathy
.
/