## Sheet1
FROM | ACTION | TARGET DATE | NOTES | STATUS | RESPONSIBILITY
TH | Repairs to roof following theft | 31st August 2024 | AJ Roofing injured, waiting on a date Pl received with RV Elliot and Co Ltd re timeline, price confirmed already | Pending | Clair
TH | Remedial Repairs to roof to claim grant | 30th September 2024 | Waiting for AJ Roofing injured cant do it | Urgent | Cathy
TH | Grant Application for Town Hall Roof | 31st August 2024 | Heritage Lottery Fund | Urgent | Cathy
TH | Report for renewal of Marriage Licence (update) | 27th August 2024 | Wedding Price List Complete | Complete | Clair
TH | Lights around stage | 30th Setmeber 2024 | Contact Hitchings to carry out a check | Pending | Clair
TH | Mayor's Parlour change of usage | 31st October 2024 | have chased St Fagans as yet no reply | Pending | Cathy/Tom