## Matters Arising
FROM | ACTION | TARGET DATE | NOTES | STATUS | RESPONSIBILITY
TH | Repairs to roof following theft | 31st August 2024 | AJ Roofing injured, waiting on a date Pl received with RV Elliot and Co Ltd re timeline, price confirmed already | Waiting on date | Clair
TH | Remedial Repairs to roof to claim grant | 30th September 2024 | Waiting for AJ Roofing | Urgent | Cathy
TH | Grant Application for Town Hall Roof | 31st August 2024 | Heritage Lottery Fund | Urgent | Cathy
L & A | Prepare tender and put out | 30th Setmeber 2024 | Approved by the Full council put out tendor when date nearer inform Edenvale First | pending | Clair/Cathy
L& A | Amend Allotment Agreement | 30th Setmeber 2024 | L & A confirmed can use Weed Killer sent over to Peter Davies | Complete | Clair
F & G | Amend Management Accounts | 30th Setmeber 2024 | Scribe not matching budget code totals | Complete | Clair
L&A | Tree Conservation Area Application (Holy Cross) | 31st August 2024 | Approved 12th Septmeber 2024 Ewart to advise on start date after speaking with Waitrose | Pending | Clair
L&A | Holy Cross Wall | 30th September 2024 | No action required until sycamore trees removed as below | Pending | Clair
TH | Report for renewal of Marriage Licence (update) | 27th August 2024 | Council aggreed so wil impliment as of 3rd September 2024 purchse license | Complete | Clair
H&S | Healthy & Safety | 31st July 2024 | Approved by full council | Urgent | Cathy
TH | Lights around stage | 30th Setmeber 2024 | Contact Hitchings to carry out a check | Pending | Clair
L & A | Area around Holycross | 30th Setmeber 2024 | Approach resident if he would be prepared to sell us the land | Pending | Clair
Full Council | Advertise Macebearer Job Description | 30th September 2024 |  | Pending | Clair
L & A | Grass Cutting now approved | 30th September 2024 | put out to tender | Complete | Cathy
TH | Renewal of Marriage License approved | 30th September 2024 | Renew and action new wedding prices | Complete | Clair
F & G | CYBER INSURANCE | 31st October 2024 | differed at last meeting | pending | Clair
F & G | TOIL POLICY | 30th September 2024 | accepted and approved | Complete | cathy
F & G | DATA RETENTION POLICY | 30th September 2024 | accepted and approved | Complete | Cathy

## Finance
FROM | ACTION | TARGET DATE | NOTES | STATUS | RESPONSIBILITY
Bank Reconcile | Monthly |  |  | Monthly | Clair
Management Accounts | Monthly |  |  | Monthly | Clair
Audit Management Accounts | Monthly |  |  | Monthly | Cathy
Audit Invoices | Monthly | VAT receipt and Reg number |  | Monthly | Clair
Chase oustanding Invoices | Monthly |  |  | Monthly | Clair

## Task & Finish Items
FROM | ACTION | TARGET DATE | NOTES | STATUS | RESPONSIBILITY
Town Hall | review and fix wooden step | 30th September 2024 | Tim hurt leg will review when recovered | Pending | Tim/Baz
Town Hall | Complete Coronation Collage | 31st August 2024 | Updated from Tom: just waiting on script writer to complete | Urgent | Tom
Town Hall | Town Council Flag | 31st July 2024 | Multiple designs on the way | Pending | Tom
Civic | Send Remembrance Sunday Diary Markers | 31st July 2024 | diary markers sent aim to send invites by end of august | Complete | Tom
Town Hall | Meet with St Fagans re Mayors Parlour | 1st Sept 2024 | Photos sent by Tom 25/07/2024, chase middle of august | Urgent | Cathy/Tom
Town Hall | Replace Projector | 30th October 2024 | Cathy has applied for a lotto grant 29th August | Pending | Cathy
L&A | Holy Cross Churchyard Maintenance | 31st December 2024 | Waiting om feedback report from Probbation team following meeting | Pending | Tim/Clair
L & A | Van Repairs | 31st August 2024 | FMG, Repairs Bridgend picking up van 28.08.24 garage has van for repairs | Ongoing | Tim/Cathy
Town Hall | Cleaning Schedule | 31st July 2024 | Given to Baz and gone through | Complete | Baz
L&A | Outdoor Maintenance Schedule | 31st July 2024 | Cathy liaise with Tim | Urgent | Tim
Town Hall | Ring Doorbell Set up | 31st July 2024 | Ring door bell missing, Tom * Tim look tomorrow 28.08.24 | Urgent | Tom
HR | Appraisal | 31st July 2024 | Cathy finalise paperwork | Pending | Cathy
FC | 5 year Plan | 31st August 2024 |  |  | Cathy
HR | Management Training | 31st August 2024 | Research suitable courses |  | Cathy
Town Hall | Report for ending set up and charging for add ons | 27th August 2024 | to be sent to the staffing committee Agenda Item | Complete | Cathy
L&A | Source quotes for new van lease | 31st August 2024 | have got 3 quotes | Complete | Clair
Governance | Add Decs of Interest document to website | 30th September 2024 | all updated and sent to Tom to add to website | Complete | Clair
Christmas | Complie list of listed buildings | 31st August 2024 | Tom has list of listed building | Complete | Tom
Christmas | Chase Graeme for decision on Christmas lights | 31st August 2024 | Emailed Graeme for an update 12th September | Pending | Tom
Christmas | Email Festive Lighting to ask for extension as no meetings in Aug | 31st August 2024 | answer is yes | complete | Tom
Training | COSHH Training for Tim and Baz | 31st August 2024 | College doesnt offer it all online will discuss best dates with Tim & Baz and book online | Pending | Clair
Training | Chainsaw Training for Tim | 31st August 2024 | confusion over if needed | Complete | Clair
Training C | First Aid Training | 31st August 2024 | All colleagues 1st October with Hands on Training Refresher Course | Complete | Clair
Civic | contact contacts and ask for quote | 30th Setmeber 2024 | get quotes for new cllr robes and hats 7 hats waiting in Ede and Ravencroft getting bak to me | pending | Clair

## Remembrance Sunday 2024
ACTION | TARGET DATE | RESPONSIBILITY | STATUS | NOTES
Diary Markers | 31/07/2024 | Tom | Complete | Complete
Invites | 31/08/2024 | Tom
First Aid | 31/07/2024 | Tom |  | Book St Johns for First Aid & March
Risk Assessments | 30/09/2024 | Tom
Town Crier |  | Tom | Complete | Confirmed
Bugler |  | Tom | Complete | Confirmed
Bagpiper |  | Tom | Complete | Confirmed
Sound System |  | Tom | Complete | Confirmed
S Wales Police Band |  | Tom | Complete | Confirmed
Air Cadets |  | Tom
Parade Marshall |  | Tom | Complete | Confirmed
Road Closure |  | Tom | Complete | Confirmed
Seating Plan for Church |  | Clair |  | will complete when I get the final numbers
Church Confirmation |  | Cathy | Complete | Complete
Order of Service |  | Heather/Duncan/Cathy |  | Meeting arranged 30/07/2024
Catering |  | Clair |  | will order as appropriate to inc any dietary requests
MaceBearers |  | Cathy/Baz |  | JD prepared for additional MB to take to Full council
Upstairs Seating/Tablewear |  | Tim/Baz